BASSANI HEALTH  |  GREEN CLOUDS  |  CANNATI  |  INTERNAL: LAUNCH TEAM

Executive Launch and Marketing Strategy

Part A: Green Clouds, online and Kyalami store, internal opening 22 October 2026

Part B: Cannati CBD, online and Kyalami, launch 1 December 2026

Prepared for Luca Liviero and Mike Stringer, and the launch team  |  3 October 2026  |  Version 2 (Lane A)  |  Working draft

Why 22 October. Luca's father would have turned 91. Green Clouds opens that day as an internal opening for the team and invited family, not a public event, and La Farmacia opens alongside it if the Department of Health visual inspection is passed in time. The companion tracker (Launch_Tracker_GC_Cannati_Oct2026.xlsx) holds every task below with owner, date and status; the goods-received form is a separate file.

1. Executive summary

- Order of work, not order of importance. Payments first, platform integration second, then licence and doctor, stock custody, member onboarding, store, and only then marketing. A beautiful store that cannot take payment or list on Budify and Cannaverse is not open.

- Payments: primary route is the Cannaverse / Budify online gateway (proven to work for this category), fallback is the Soundroom card portal. Both tested with a sale, a refund and a failed card by 14 October, settling into a separate Green Clouds account.

- Integration: product listings live in both portals by 15 October from a product file; full API sync (stock, orders, members) follows as phase 1.5 by 13 November. Budify POS is the single source of stock truth.

- The model (Lane A, decided 3 October): Green Clouds is a members' club with a medical engine. Seknd Nature's look and membership mechanics on the outside; underneath, Dr Peter Makhambeni on site (Licence to Dispense GP00531D-2) decides every prescription after a real consult, files the Section 21, and dispenses. Prescription products are invoiced by the dispenser, with the Green Clouds wallet collecting on its behalf. No collective structure on Bassani stock.

- Website: built by Alex (Subtract Digital) to the Lane A brief. The must-have is a free registration gateway: visitors see no product prices; anyone who registers free (cell code, SA ID number, 18+) sees the menu, prices and a working cart; checkout unlocks only after Dr Peter approves, and only for what is on the script.

- Membership and the R450: Pay-as-you-go, Green R1,000, Cloud R2,500, Sky R5,000 as prepaid wallet credit. The SAHPRA fee is per patient per approval, about R75 a month; R34 a basket for Green, R13.50 for Cloud. Bonus credit applies to non-prescription items only (Medicines Act s18A).

- Green Clouds go-to-market: "Licensed. Lab-tested. Doctor on site." Members-only, organic channels: WhatsApp community, Budify and Cannaverse store pages, referral, education evenings with Dr Peter. No paid Meta or Google ads, no public billboards, nothing that links La Farmacia to Green Clouds. Member trading ramp from 5 November.

- Cannati go-to-market: "Fewer things, done properly." Launch 1 December into the Christmas window: web shop, Kyalami display, gift sets, sampling, Antoinette's accounts, and buyer meetings with Wellness Warehouse, Dis-Chem, Faithful to Nature, Clicks (adult range) and Pet Heaven for shelves in Q1 2027. Drinks sell first in Green Clouds' own channels.

- Money: R80,000 launch budget each, allocated below and tracked against actuals in the workbook.

- Biggest risks: payment switch-off, API slippage, Dr Peter's start date and consult capacity, the licence premises address, counsel's view on prices to registered users and tier bonuses, and any publicity tying La Farmacia to Green Clouds.

2. Team and how we run the launch

| Owner | Role in the launches |
| --- | --- |
| Luca Liviero | Chairman: final sign-off, founding members, club paperwork |
| Mike Stringer | Final sign-off with Luca |
| Benny | CFO: payments, gateways, bank and settlement |
| Lilanie | Finance: POS pricing, reconciliation, cash handling |
| Mark | Store manager: store, staff, receiving, delivery |
| Dr Peter Makhambeni | Doctor on site: consultations, prescriptions, dispensing under licence GP00531D-2 |
| Ray | Store and La Farmacia completion; DOH inspection readiness |
| Henk Krebs | QA and compliance: SOPs, licences, consent, COAs |
| Tristan Hutchings | Product, stock, pricing data, transfers |
| Antoinette Kriel (ANTZ) | Marketing, brand, content, web, trade sell-in (Cannati) |
| Nick (Cannaverse) | Cannaverse portal, payment gateway, API |
| Budify | POS, marketplace listing, payment gateway, API |

- Weekly launch stand-up: Mondays 08:30, 30 minutes, run from the Dashboard tab. Each owner updates their Status column before the meeting.

- Daily huddle from 19 October: 15 minutes at 08:00 in the store until 22 October.

- Sign-off gates: shop sign-off 19 October (Luca, Mike, Ray, Mark); dry run 20 October; go / no-go 21 October (Luca and Mike).

PART A  |  GREEN CLOUDS: ONLINE AND KYALAMI STORE

Internal opening Thursday 22 October 2026. Member trading ramp from Thursday 5 November.

A1. What must be true by 22 October

| Workstream | What must be true | Owners | By |
| --- | --- | --- | --- |
| Payments | Two payment routes live and tested (gateway + Soundroom); separate settlement account; receipts correct; cash policy | Benny, Lilanie | 16 Oct |
| Systems | Budify POS installed; listings live; website with free registration gateway, wallet and members' area tested; staging locked; legal hub; API in phase 1.5 | Mark, Tristan, Budify, Nick, Henk, Antoinette, Luca | 19 Oct |
| Store | Snags closed; signage with separate GC and La Farmacia entrances; TV loop; coffee machine; waiting area; private consult room; security and safety; shop sign-off | Ray, Mark, Luca | 19 Oct |
| Clinical | Dr Peter's days and consult fees fixed; licence address confirmed; AI pre-screen draft-only; end-to-end test patient done; Section 21 expiry register; La Farmacia inspection passed | Henk, Ray, Benny | 19 Oct |
| Club | Lane A decided; membership terms v0.2 through counsel; tiers in the wallet; R450 by tier decided; age checks in store and on delivery; founding member list | Luca, Henk, Mark, Lilanie | 16 Oct |
| Stock | Opening stock transferred and received on signed GRNs with COAs; stock room and display ready | Tristan, Mark | 19 Oct |
| Delivery | Own driver for Zone A plus a courier that accepts the product; discreet packaging; zones and fees live online | Mark, Tristan, Antoinette | 16 Oct |
| People | Staff trained (product, POS, compliance); dry run; go / no-go; opening | Mark, Luca | 22 Oct |
| Marketing | Menu and boxes signed off; content shoot; WhatsApp community; portal pages; referral programme; opening moment | Antoinette, Tristan, Lilanie, Luca | 22 Oct |

Top priorities this week (5 to 9 October)

- 7 Oct | Benny: Merchant onboarding with the Cannaverse / Budify online payment gateway: documents submitted for the Green Clouds entity

- 7 Oct | Budify: Budify API scoping call: endpoints, credentials, stock and order sync, member data

- 7 Oct | Nick: Cannaverse integration scoping call: listing feed, orders, payments, member portal

- 7 Oct | Henk: Licence premises address checked: licence reads 12 Marcus Street, Barbecue Downs; BH address is Cnr Dytchley and Marcius Roads

- 7 Oct | Antoinette: Staging locked (password on every page, noindex) and brief section 2 fixes done (Cannati and THC soda off, title, copy)

- 7 Oct | Antoinette: Alex's reply: plugin proposal with costs, hosting proposal, quote and timeline

- 8 Oct | Tristan: Product master data loaded: SKU codes, names (5 strain carts incl. Pineapple Express cart only), barcodes, prices, R250 transfer cost

- 9 Oct | Benny: Separate Green Clouds settlement bank account confirmed; daily reconciliation routine written

- 9 Oct | Mark: Budify POS hardware installed: tablet, receipt printer, scanner, cash drawer, card device

- 9 Oct | Henk: Dr Peter move-in date, alterations and days per week agreed

- 9 Oct | Benny: Stock custody decided and documented: BH stock displayed at GC (consignment) or sold to GC at R250 per cart (tax invoice)

- 9 Oct | Luca: Club constitution and membership terms located or drafted

- 9 Oct | Tristan: Final signed-off boxes uploaded; sticker fixes (CAARTRIDGE typo, batch and QR label)

- 9 Oct | Luca: Site map, wireframes and plugin list approved

- 9 Oct | Henk: Dr Peter's consult fees (first and renewal) set; booking with video; fee identical whether or not he prescribes

A2. Countdown

| Week | Focus |
| --- | --- |
| 5 to 9 Oct | Staging locked and Alex's proposal (7 Oct); site map approved; payments onboarding; POS; licence address; Dr Peter's schedule and consult fees; seller of record; box sign-off |
| 12 to 16 Oct | Wallet and gateway test (12); counsel on terms (14); free registration gateway live (14); end-to-end test patient (16); listings live; snags, signage, security; La Farmacia inspection; stock on GRNs; content shoot |
| 19 to 21 Oct | Dr Peter on site, TV loop and display, staff training, shop sign-off (19), dry run (20), go / no-go (21) |
| 22 Oct | Internal opening honouring Luca's father; La Farmacia opens if inspection passed |
| 26 Oct to 4 Nov | Members-only trading, feedback, fix list |
| From 5 Nov | Member trading ramp: broadcast, referral push, education evening 1; API live by 13 Nov; 30-day review 20 Nov |

A3. Positioning and proposition

Positioning line. Licensed. Lab-tested. Doctor on site. The competitor study found that almost no Gauteng seller shows potency or lab certificates as standard, and none has a doctor in the building. That is the gap Green Clouds owns.

- Trust: potency and batch on every pack, QR to the COA (fix the stickers: add batch and QR, correct "CAARTRIDGE").

- Care: consultation with Dr Peter, private consult room, education evenings.

- Convenience: same-day Zone A delivery at R60 (free over R750), 30-minute click and collect, online ordering through Budify, Cannaverse and the web shop.

- Experience: coffee, a proper waiting lounge, a TV loop that teaches rather than sells, staff who know the product.

- Membership: prepaid tiers with free deliveries and perks; R100 for R100 referral once the friend is approved; lounge and education evenings for members.

- Range: five Green Clouds strain cartridges (Pineapple Express, Durban Poison, Northern Lights, Alaskan Thunder, Lemon Cherry Gelato) at R650 against a BH transfer price of R250, plus flower, pre-rolls, edibles, the nano soda and accessories from the launch menu.

A4. Who we are for

| Audience | Why they come | How we reach them |
| --- | --- | --- |
| Existing Bassani Section 21 patients | Continuity of care, convenience, a doctor they can see | Direct invitation via Dr Peter and the patient list (with consent) |
| Adults 25 to 55 in Kyalami, Midrand, Fourways, Sunninghill | Trusted, local, lab-tested supply with delivery | Referral, WhatsApp community, estate and business networks, word of mouth |
| Budify and Cannaverse users | Already buying online in the category | Store pages, featured placement, portal promotions |
| Wellness-curious first-timers | Want guidance before they try | Education evenings, low-dose products, consult first |

A5. Channels: what we do and what we do not do

| Do | Do not |
| --- | --- |
| WhatsApp Business: catalogue, members' community, broadcast with opt-in | Paid Meta, Instagram, TikTok or Google ads (banned for THC; risks the accounts) |
| Budify and Cannaverse store pages and featured placement | Public billboards, flyers or street signage advertising THC |
| Member referral: R100 for R100 once the friend is approved, usable on non-prescription items | Any health or cure claims |
| Free registration: prices and cart for registered users | Product prices or images on public pages, posts or adverts |
| Education evenings with Dr Peter (members only) | Any post, sign or event that links La Farmacia to Green Clouds |
| Organic content: store, team, process, lab results | Selling to anyone not onboarded and verified 18+ |
| Micro-creators who are members, posting organically | Delivery without an ID check at the door |

A6. The member journey

- 1. Discover: Referral, WhatsApp, portal pages, Dr Peter. Public site shows the experience, tier prices and the consult fee, not product prices.

- 2. Register free: Cell code, email, SA ID number checked for 18+, terms accepted. Menu, prices and cart unlock; checkout locked.

- 3. Apply: ID and selfie, health consent, Section 21 questionnaire. Software sorts the answers for Dr Peter; it decides nothing.

- 4. Consult: 10 to 15 minutes, video or in person; member pays Dr Peter's fee, the same whether or not he prescribes.

- 5. Approval: Dr Peter prescribes and files the Section 21; on approval the member's products and monthly limits load and checkout opens.

- 6. Tier and order: Member picks a tier, tops up the wallet, orders from their script; dispenser invoices.

- 7. Receive: Collect with ID, or same-day delivery with ID check and signed hand-over.

- 8. Renew: Reminder at month five; follow-up consult; new Section 21.

Membership tiers and the R450 (from the cost model)

| Per member per month | Pay-as-you-go | Green | Cloud | Sky |
| --- | --- | --- | --- | --- |
| Spend | R450 | R1,000 | R2,500 | R5,000 |
| R450 Section 21 fee per basket | R75 | R34 | R13.50 | R6.75 |
| Who pays the R450 (proposed) | Member | Member | Included | Included |
| Member's monthly cost of staying legal (fee + renewal consult) | R117 | R117 | R42 | R42 |
| Contribution after compliance | 51% | 42% | 40% | 37% |

At 200 members (100 / 60 / 30 / 10): about R230,000 revenue a month at 42% contribution, roughly 73 Section 21 applications and consults a month while growing, about 4 hours of Dr Peter's time a week. Assumptions (consult fees, margins, six-month validity) to confirm; the workbook is GC_LaneA_Member_Journey_Cost_Model_v1.

A7. Budget: R80,000

| Line | Detail | Budget |
| --- | --- | --- |
| Launch content and photography | Store, product and team shoot; short videos for WhatsApp and portals | R12,000 |
| In-store: TV loop, menus, shelf talkers, signage extras | Print and screen content | R10,000 |
| Portal visibility: Budify and Cannaverse featured placement | Paid placement where offered | R15,000 |
| WhatsApp Business / SMS platform | Broadcast tool, three months | R5,000 |
| Founding member and referral incentives | Product at cost and vouchers | R15,000 |
| Education evenings with Dr Peter (x3) | Members only, Kyalami | R9,000 |
| Micro-creators and community partners | Members-only content, no paid social ads | R8,000 |
| Contingency |  | R6,000 |
| Total |  | R80,000 |

A8. KPIs (proposed, agree at the 30-day review)

| KPI | Target | Source |
| --- | --- | --- |
| Members onboarded | 120 by 30 Nov | Budify / onboarding log |
| Conversion: members who buy in first 14 days | 60% | POS |
| Average basket | R450 | POS |
| Repeat purchase within 30 days | 35% | POS |
| Online share of sales | 30% | Portals / web |
| Referral share of new members | 25% | Referral codes |
| Payment failure rate | Under 3% | Gateway reports |

PART B  |  CANNATI CBD: ONLINE AND KYALAMI

Launch Tuesday 1 December 2026. Christmas window, then chain shelves in Q1 2027.

B1. What must be true by 1 December

| Gate | What must be true | Owner | By |
| --- | --- | --- | --- |
| CN-01 | SAHPRA regulatory pharmacist engaged; labels, leaflet and claims signed off | Henk | 30 Oct |
| CN-02 | Manufacturer s22C licence covers drops and gummies; GMP batch records | Henk | 23 Oct |
| CN-03 | Cannati schedule in the Greenclouds agreement amended from Section 21 to OTC CBD only | Luca | 30 Oct |
| CN-04 | External CBD and nano suppliers certify THC below 0.001% per lot; ask nano partner if it processes THC | Henk | 6 Nov |
| CN-05 | COA per batch with QR code on every pack | Henk | 13 Nov |
| CN-06 | Pet: written query to SAHPRA (VETqueries@sahpra.org.za) on Schedule 0 for animals | Henk | 9 Oct |
| CN-07 | Drinks: supplier emulsion stability data plus finished-pack shelf-life and liner test started | Henk | 6 Nov |
| CN-08 | Unit costs run through the Cannati price waterfall; prices locked | Tristan | 30 Oct |
| CN-09 | Packaging artwork with Cannati logo: drops, gummies, drinks, pet, Discovery Pack, gift box | Antoinette | 30 Oct |
| CN-10 | Print and component orders placed (bottles, droppers, child-resistant jars, cans, labels) | Tristan | 6 Nov |
| CN-11 | First production runs released by QA (3rd floor CBD area) | Henk | 20 Nov |
| CN-12 | Goods received on the GRN sheet with COAs | Mark | 24 Nov |

Range at launch. Drops (Daily and Night 600mg), Gummies (Daily and Night 30 x 10mg, Discovery Pack 10 x 10mg), Drinks (Water 500ml, Soda Tropical and Berry 330ml, 4-pack, all 5mg nano CBD), Pet (dog 600mg, cat 300mg). Softgels follow in Phase 2. Every pack: three permitted claims only, "Adults only", the SAHPRA unregistered-medicine disclaimer, batch and COA QR. No bioavailability or equivalence claims.

B2. Positioning and channels

- Line: "Fewer things, done properly." Clean, clearly dosed, THC-free, made in South Africa, every batch tested.

- Christmas: three gift sets (Daily: drops and gummies; Night: drops and gummies; Pet) at the Kyalami store, web shop and with Antoinette's accounts.

- Antoinette's accounts: the Natural Elixir network sells Cannati alongside the Elixir range. Agree the drinks positioning with Martin McHale first (Cannati 330ml soda and 500ml water versus the Natural Elixir 750ml tonic).

- Chains (Q1 2027 shelves): buyer meetings by 27 November with Wellness Warehouse, Dis-Chem, Faithful to Nature, Clicks (adult Discovery Pack and Daily Gummies, not a children's product) and Pet Heaven. Lead with drops, gummies and pet; gummies are the format no chain stocks today.

- Green Clouds members: first access to Cannati drinks and a member launch offer.

- Sampling: about 400 Discovery Packs for buyers, staff, members and the media breakfast.

- Content and PR: education-led, claims-checked by Henk before anything is published. Paid social for CBD stays off for now.

B3. Channel and trade tasks

| Task | Owner | By |
| --- | --- | --- |
| Cannati web shop pages, checkout and delivery (R70, free over R500) | Antoinette | 20 Nov |
| Payment gateway for CBD confirmed (mainstream gateways usually accept CBD; confirm) | Benny | 13 Nov |
| Cannati SKUs loaded in Budify POS and portals | Lilanie | 24 Nov |
| Kyalami Cannati display and shelf talkers | Mark | 27 Nov |
| Antoinette's accounts list (Natural Elixir network) and sell-in plan | Antoinette | 6 Nov |
| Trade presenter, price list and sample kits | Antoinette | 13 Nov |
| Buyer meetings: Wellness Warehouse, Dis-Chem, Faithful to Nature, Clicks (adult range), Pet Heaven | Antoinette | 27 Nov |
| Agree Cannati drinks positioning with Martin McHale (Natural Elixir tonic) | Luca | 23 Oct |
| Christmas gift sets: Daily Drops + Gummies; Night set; Pet set | Antoinette | 13 Nov |
| Brand content: photography, education posts, launch film | Antoinette | 20 Nov |
| PR: wellness media and trade press release (claims-checked) | Antoinette | 24 Nov |
| Launch day 1 December: web shop live, Kyalami display, sampling, member offer | Antoinette | 1 Dec |
| 30-day review incl. Christmas sell-through and chain feedback | Luca | 18 Dec |

B4. Budget: R80,000

| Line | Detail | Budget |
| --- | --- | --- |
| Brand content and photography | Pack shots, lifestyle, launch film | R12,000 |
| Sampling: Discovery Packs at cost | About 400 packs for trade, staff, members | R16,000 |
| Trade presenter, samples and buyer kits | Wellness Warehouse, Dis-Chem, FtN, Clicks, Pet Heaven | R8,000 |
| PR and trade / media breakfast | Kyalami, claims-checked | R12,000 |
| Web shop pages, SEO and email | Cannati pages and launch emails | R10,000 |
| Wellness creators (claims-checked) | Organic content; no paid social ads for now | R10,000 |
| In-store display and gift-set packaging | Kyalami display; gift boxes | R6,000 |
| Contingency |  | R6,000 |
| Total |  | R80,000 |

B5. KPIs (proposed)

| KPI | Target | Source |
| --- | --- | --- |
| Trade accounts listed | 10 by 31 Jan 2027 | Account list |
| Web and Kyalami units sold in December | 1,000 | POS / web |
| Gift sets sold | 150 | POS |
| Discovery Pack to full-size conversion | 20% | Codes |
| Chain buyer meetings held | 5 by 15 Dec | Meeting log |
| Sell-through at accounts (first 60 days) | 40% | Account reports |

C. Risks

| Risk | Launch | Rating | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| Payments switched off or refused for THC | GC | High | Two routes live and tested (Cannaverse/Budify gateway and Soundroom); cash procedure; settle daily | Benny |
| API integration not ready by 22 Oct | GC | High | Launch on product file / manual listings; API as phase 1.5 by 13 Nov | Nick |
| Dr Peter start slips past 22 Oct | GC | High | Confirm date by 9 Oct; agree interim prescribing cover | Henk |
| Licence premises address mismatch (Marcus vs Marcius; Barbecue vs Barbeque) | GC | High | Check with DOH now; amend before inspection | Henk |
| La Farmacia associated with Green Clouds in any publicity | GC | High | Internal opening only; separate signage, entrances, posts | Luca |
| Stock title unclear between BH and GC | GC | High | Decide consignment vs sale at R250; document and invoice | Benny |
| Courier refuses product | GC | Medium | Own driver Zone A; second courier; locker option off | Mark |
| Member data shared without consent | Both | Medium | POPIA consent in onboarding; data-sharing terms with platforms | Henk |
| Cannati labels not signed off in time | Cannati | High | Engage RP by 16 Oct; freeze claims; 3 permitted claims only | Henk |
| Cannati drinks stability or margin | Cannati | Medium | Supplier data; finished-pack test; sell in GC channels first | Henk |
| Natural Elixir overlap on drinks | Cannati | Medium | Agree positioning with Martin by 23 Oct | Luca |
| Chain buyers cautious of leaf logo / grey parent | Cannati | Medium | Wordmark-only pack option; lead with compliant SKUs | Antoinette |
| Staging site reachable without login | GC | High | Password on every page, noindex; logged-out check by Antoinette (GC-58) | Antoinette |
| Tier bonuses treated as an incentive on medicines (s18A) | GC | High | Bonus and referral credit on non-prescription items only; counsel review (GC-57) | Henk |
| Prices shown to registered non-patients read as advertising (s18) | GC | Medium | Free registration with ID-number check; no public product prices; counsel review | Henk |
| Dr Peter's capacity: about 70 consults a month at 200 members | GC | Medium | Video consults of 10 to 15 minutes; second prescriber (Dr Maharaj) as back-up | Henk |
| AI script drafting seen as automated prescribing | GC | High | Draft-only tool; doctor's decision and words on every file; no per-script fee | Henk |

D. Decisions needed

| Decision | Who decides | Needed by |
| --- | --- | --- |
| Stock custody: consignment display or sale to GC at R250 per cart | Benny / Luca | 9 Oct |
| When GC opens to members beyond the internal opening (suggested 5 Nov) | Luca / Mike | 16 Oct |
| Licence premises address: confirm or amend | Henk | 7 Oct |
| Club paperwork: existing documents or new draft | Luca | 9 Oct |
| Online listing name for Alaskan Thunder F*ck | Antoinette | 12 Oct |
| Green Clouds logo master colour (lime or dark green) | Luca / Antoinette | 9 Oct |
| Cannati drinks positioning with Martin McHale | Luca | 23 Oct |
| Cannati chain packaging: leaf logo or wordmark only | Luca / Antoinette | 30 Oct |
| Lane A: medical front of house (taken 3 Oct) | Luca | Done |
| Prices: free registration gateway, no public product prices (taken 3 Oct) | Luca | Done |
| R450 by tier: member pays or included | Luca / Benny | 14 Oct |
| Seller of record for prescription products: dispenser, Green Clouds as collection agent | Benny / Henk | 12 Oct |
| Dr Peter's consult fees | Dr Peter / Henk | 9 Oct |

E. The launch pack

- Launch_Tracker_GC_Cannati_Oct2026.xlsx: dashboard, both tick sheets, marketing calendar, budgets, KPIs, team, risks, decisions.

- Goods_Received_Note_GRN_Kyalami.xlsx: printable GRN form and GRN log (separate, for Mark and Tristan).

- Green Clouds launch menu v2 and price list v2; Cannati menu v3 and range workbook v2 (already filed).

- Lane A Website folder: website build brief v1.1 (sent to Alex 3 Oct), Green Clouds membership terms draft v0.2, member journey and cost model.

- Club Model Reference: Seknd Nature benchmark memo.

- To come: counsel sign-off, final signed-off boxes, delivery partner terms, Dr Peter's clinic schedule and fees.